## Planning
Week # | Entity | Category | Plan ID | Activity | Scheduled | Priority | Status | Notes
1 | Hotel Co 51 | 1. Maintain Governance Structure | HC51-01 | Formally appoint the Captains as Privacy Champions. | Q1 | 2 | Planned | Assess whether the Privacy Champions will be at a hotel level or HQ level
2 | Hotel Co 51 | 2. Maintain Personal Data Inventory | HC51-03 | Update record of processing activities for hotels & HQ. | Q1 | 2 | Planned
4 | Vastint | 3. Awareness & training | VAS-06 | Provide regular training sessions to all Privacy Champions. | Q1 | 2 | Planned
5 | Vastint | 3. Awareness & training | VAS-07 | Regularly share privacy content via newsletters and intranet. | Q1 | 3 | Planned
6 | Hotel Co 51 | 4. Embed Data Privacy Into Operations | HC51-05 | Add Data about food allergies and/or intolerances to the policy. | Q1 | 1 | Planned
7 | Hotel Co 51 | 7. Manage Third-Party Risk | HC51-11 | Perform privacy compliance check for existing vendors. | Q1 | 1 | Planned
8 | Vastint | 4. Privacy notices & Privacy policy | VAS-08 | Produce Data Retention Policy including retention scheme for all counties/ent... | Q1 | 1 | Planned
9 | Vastint | 5. Data Privacy in Operations | VAS-10 | Implement data retention policy by checking systems for old data and deleting... | Q1 | 1 | Planned
10 | Vastint | 7. 3rd Party Risk (vendors) | VAS-14 | Check existing vendors on compliance with the GDPR and the DPA. | Q1 | 1 | Planned
11 | Vastint | 10. Data Breach Management | VAS-18 | Clarify the data breach flow and define roles & responsibilities. | Q1 | 1 | Planned
12 | Hotel Co 51 | 1. Maintain Governance Structure | HC51-02 | Reassess the need for a DPO on Hotel Co 51 level. | Q1 | 3 | Planned
13 | Vastint | 1. Privacy Governance & reporting | VAS-02 | Reassess the positioning of the DPO for all legal entities. | Q1 | 3 | Planned
14 | Hotel Co 51 | 4. Embed Data Privacy Into Operations | HC51-06 | Check consent collection process via the Registration Cards. | Q2 | 2 | Planned
15 | Hotel Co 51 | 4. Embed Data Privacy Into Operations | HC51-07 | Make action plan based on the provided self-assessment | Q2 | 2 | Planned
16 | Vastint | 2. Records of Processing Activities | VAS-03 | Arrange a ‘deep dive’ for each entity to assess completeness. | Q2 | 2 | Planned
17 | Vastint | 5. Data Privacy in Operations | VAS-11 | Create a CCTV inventory with all supporting documentation. Make changes to th... | Q2 | 2 | Planned
18 | Vastint | 11. Monitoring Data Privacy & identify external criteria | VAS-20 | Perform topdown check of compliance with the policies. | Q2 | 2 | Planned
19 | Hotel Co 51 | 4. Embed Data Privacy Into Operations | HC51-08 | Add retention of emails to the retention policy. | Q3 | 2 | Planned
20 | Hotel Co 51 | 5. Maintain Training and Awareness Program | HC51-09 | Make GDPR training mandatory and enforce it. | Q3 | 2 | Planned
21 | Hotel Co 51 | 7. Manage Third-Party Risk | HC51-12 | Make vendor privacy audit questionaire. | Q3 | 2 | Planned
22 | Hotel Co 51 | 7. Manage Third-Party Risk | HC51-13 | Check if long term data processing agreements comply with new privacy rules. | Q3 | 2 | Planned
23 | Vastint | 3. Awareness & training | VAS-05 | Make annual GDPR training mandatory for all staff and enforce it. | Q3 | 2 | Planned
24 | Vastint | 9. Privacy by Design & Default and DPIA | VAS-16 | Check if all necessary DPIAs are being performed. | Q3 | 2 | Planned
25 | Vastint | 9. Privacy by Design & Default and DPIA | VAS-17 | Check if results from DPIAs are implemented. | Q3 | 2 | Planned
26 | Hotel Co 51 | 3. Maintain Internal Data Privacy Policy | HC51-04 | Produce AI policy. | Q4 | 3 | Planned
27 | Hotel Co 51 | 12. Monitor Data Handling Practices | HC51-18 | Implement annual Hotel GDPR Self Assessment | Q4 | 3 | Planned
28 | Vastint | 2. Records of Processing Activities | VAS-04 | Perform annual check of the RoPA for each entity. | Q4 | 3 | Planned
29 | Vastint | 4. Privacy notices & Privacy policy | VAS-09 | Produce AI policy. | Q4 | 3 | Planned
30 | Vastint | 7. 3rd Party Risk (vendors) | VAS-13 | Create central repository for all Data Processing Agreements for all procured... | Q4 | 3 | Planned
31 | Vastint | 11. Monitoring Data Privacy & identify external criteria | VAS-19 | Implement annual GDPR Self Assessment for Privacy Champions | Q4 | 3 | Planned