## Vastint
| Action plan 2026 Vastint | [6 empty] | visualise the running business on top of projecs
| Privacy activities | Impact | Probability | Risk | Prio | Scheduled | Owner | Lucas does this include activites in our kanban board?
1. Privacy Governance & reporting
1 | Holding and recently created entities do not have a Privacy Champion yet. | Medium | Medium | Medium | 2 | In progress |  | does this mean that Hospitality and Hotel Co had champions until now (neither of the are recently created)
2 | Reassess the positioning of the DPO for all legal entities. | Low | Low | Low | 3 | Q1 |  | we are missing the proposal for the privacy governance structure
2. Records of Processing Activities
3 | Arrange a ‘deep dive’ for each entity to assess completeness. | Medium | Low | Medium | 2 | Q2 |  | Completeness of what?
4 | Perform annual check of the RoPA for each entity. | Low | Low | Low | 3 | Q4
3. Awareness & training
5 | Make annual GDPR training mandatory for all staff and enforce it. | Medium | Medium | Medium | 2 | Q3
6 | Provide regular training sessions to all Privacy Champions. | Medium | Medium | Medium | 2 | In progress
7 | Regularly share privacy content via newsletters and intranet. | Low | Low | Low | 3 | In progress
4. Privacy notices & Privacy policy
8 | Produce Data Retention Policy including retention scheme for all counties/entities. | High | High | High | 1 | Q1
9 | Produce AI policy. | Low | Low | Low | 3 | Q4 |  | Low or medium?
5. Data Privacy in Operations
10 | Implement data retention policy by checking systems for old data and deleting them. | High | High | High | 1 | Q1 |  | interface data governance managers | we can adapt the hotel co 51 retention policy
11 | Create a CCTV inventory with all supporting documentation. Make changes to the CCTV systems where necessary. | Low | High | Medium | 2 | Q2 |  | is this high risk? Who does what here It vs privacy champions
6. IT Security Risks
12 | Managed by CISO. | - | - | - | - | - | -
7. 3rd Party Risk (vendors)
13 | Create central repository for all Data Processing Agreements for all procured systems, applications and services. | Low | Low | Low | 3 | Q4 |  | this is what we are doing on Teams, right?
14 | Check existing vendors on compliance with the GDPR and the DPA. | High | Medium | High | 1 | Q1 |  | what does this mean in practice?
8. Rights of Data Subjects
15 | No action | - | - | - | - | - | - | this is an ongoing task right?
9. Privacy by Design & Default and DPIA
16 | Check if all necessary DPIAs are being performed. | High | Low | Medium | 2 | Q3 |  | does this include existing systems?
17 | Check if results from DPIAs are implemented. | High | Low | Medium | 2 | Q3
10. Data Breach Management
18 | Clarify the data breach flow and define roles & responsibilities. | High | Medium | High | 1 | Q1
11. Monitoring Data Privacy & identify external criteria
19 | Implement annual GDPR Self Assessment for Privacy Champions | Low | Low | Low | 3 | Q4
20 | Perform topdown check of compliance with the policies. | Medium | Medium | Medium | 2 | Q2

## Hotel Co 51
Action plan 2026 Hotel Co 51
| Privacy activities | Impact | Probability | Risk | Prio | Scheduled | Comments | Owner
1. Maintain Governance Structure
1 | Formally appoint the Captains as Privacy Champions. | Medium | Medium | Medium | 2 | In progress
2 | Reassess the need for a DPO on Hotel Co 51 level. | Low | Low | Low | 3 | DONE
2. Maintain Personal Data Inventory
3 | Update record of processing activities for hotels & HQ. | Medium | Low | Medium | 2 | In progress | Hotel RoPAs to be sent together with one-pager guidance
3. Maintain Internal Data Privacy Policy
4 | Produce AI policy. | Low | Low | Low | 3 | Q4 | Interogo is taking care.
4. Embed Data Privacy Into Operations
5 | Add Data about food allergies and/or intolerances to the policy. | High | Medium | High | 1 | Q1
6 | Check consent collection process via the Registration Cards. | Low | High | Medium | 2 | Q2
7 | Make actionplan based on the provided information. | Medium | Medium | Medium | 2 | Q2
8 | Add retention of emails to the retention policy. | Low | High | Medium | 2 | Q3
5. Maintain Training and Awareness Program
9 | Make GDPR training mandatory and enforce it. | Medium | Medium | Medium | 2 | Q3
6. Manage Information Security Risk
10 | Managed by CISO. | - | - | - | - | - |  | -
7. Manage Third-Party Risk
11 | Perform privacy compliance check for existing vendors. | High | Medium | High | 1 | Q1
12 | Make vendor privacy audit questionaire. | Medium | Low | Medium | 2 | Q3
13 | Check if long term data processing agreements comply with new privacy rules. | Medium | Medium | Medium | 2 | Q3
8. Maintain Notices
14 | No action | - | - | - | - | - |  | -
9. Respond to Requests and Complaints from Individuals
15 | No action | - | - | - | - | - |  | -
10. Monitor for New Operational Practices
16 | No action | - | - | - | - | - |  | -
11. Maintain Data Privacy Breach Management Program
17 | No action | - | - | - | - | - |  | -
12. Monitor Data Handling Practices
18 | Implement annual Hotel GDPR Self Assessment | Low | Low | Low | 3 | Q4
13. Track External Criteria
19 | No action | - | - | - | - | - |  | -